## Implementation Workplan
___________ First Nation |  | Last updated: insert date |  |  | Prepared by:____________________
CD = Capacity Development
SAC = Standards and Certification
Financial Management System Certification Implementation Work Plan
Reference | Milestone/Task | Responsible Party | Completion Date | Complete? | Comments
1 | Phase 1 - Getting Started
1.1 | Initial Readiness Assessment | CD Manager/Senior Management | September 1, 2017 | Yes
1.2 | Work Plan | Senior Management/CD Manager | September 1, 2017 | Yes
1.3 | FAL Update | First Nation/CD Manager
1.4 | Council approval of FAL update | First Nation/CD Manager
2 | Phase 2 - Policy Development and Implementation
2.1 | Drafting Governance policy (CD Manager Sample) | Senior Management/CD Manager
2.2 | Draft Annual Conflict of Interest Disclosure for Council/Sr. Management/FAC | Senior Management/CD Manager
2.3 | Draft Delegation of Authority (if separate from Governance policy) | Senior Management/CD Manager
2.4 | Draft FAC Terms of Reference, including eligibility criteria | Senior Management/CD Manager
2.5 | Council approval of 2.1 - 2.13 above | Council
2.6 | Documented process for updating, reviewing and approving these financial policies, reporting of remuneration and expenses, 5-year financial plan, contract and tendering procedures for capital projects, development and approval timing of strategic plans, multi-year financial plans, tangible capital projects and annual budget | Senior Management/Consultant
2.7 | Draft HR Policy, including code of conduct and whistleblower policy | Senior Management/CD Manager
2.8 | Draft Finance Policy (using CD Manager sample) | Senior Management/CD Manager
2.9 | Draft Information Management Policy (use CD Manager sample) | Senior Management/CD Manager
2.1 | Council approval of Finance/HR/Information Management Policies | Council
2.11 | Policy Desk Review by Capacity Development Manager | CD Manager
2.12 | Formal Policy Desk Review by Standards and Certification team | SAC Manager
3 | Phase 3 - FMS Implementation
3.1 | Training on Governance Policy | CD Manager/First Nation
3.2 | Training on Information Management Policy | CD Manager/First Nation
3.3 | Training on Finance Policy | CD Manager/First Nation
3.4 | Training on HR Policy | CD Manager/First Nation
3.5 | Implement core elements of FAL and provide to CD Manager:
| Finance and Audit Committee (FAC) Terms of Reference | First Nation
| Finance and Audit Committee (FAC) meeting minutes | First Nation
| Most recent strategic plan | First Nation
| Copy of current organization chart | First Nation
| Sample of a completed (signed) conflict of interest disclosure statement for Councillor, FAC member and employee | First Nation
| Most recent audited financial statements and schedule of Council remuneration and proof of approval by Council no later than July 29 | First Nation
| Most recent budget and proof of approval by Council no later than March 31 | First Nation
| Most recent multi-year financial plan (5 years) that links to your strategic and capital plans | First Nation
| Most recent capital project plan | First Nation
| Community reporting package, power point slides, etc. to confirm that members have been informed of the annual budget, multi-year financial plan, capital projects and borrowings for capital projects | First Nation
| Most recent annual report and proof of being published no later than September 27 | First Nation
| Most recent asset register and life-cycle management plan | First Nation
| Most recent quarterly report | First Nation
| Most recent bank reconciliation | First Nation
| Most recent risk register including risk management plan | First Nation
3.6 | Complete Final FMS Readiness Assessment | CD Manager/Senior Management
3.7 | Review any risk-based FMS testing requirements | CD Manager/Senior Management
3.8 | Complete and submit any final required documentation | Senior Management
3.9 | Have introductory meeting with Senior Management, CD Manager and SAC Manager | Senior Management/CD Manager/SAC Manager
4 | FMS Certification Testing
4 | Meet or have call to schedule FMS Certification on-site testing | First Nation/SAC Manager
4.1 | FMS Certification Testing | First Nation/SAC Manager
4.2 | Submit any final required documentation | First Nation
4.3 | Compile and assess testing results | SAC Manager
4.4 | Review testing results | SAC Manager/First Nation/CD Manager (as necessary)
4.5 | Subsequent events procedures | SAC Manager/First Nation
4.6 | Quality assurance review | SAC Team
4.7 | Formal review of compliance with FMS Standards | SAC Team
4.8 | Board Review and Approval | FMB
4.9 | Issue FMS Certificate, Report and Schedule | FMB